## Sheet1
Sr.No | ESXi Build checklist | Status (Yes/No) | Artifacts Required (yes /no) | Comments
1 | Racking and Stacking for Cisco UCS Server | Yes | No
2 | CIMC configuration (IP, CIMC Name, DNS & Standard CIMC Password) | Yes | No
3 | DNS Records creations for CIMC & ESXi servers | Yes | Yes
4 | Verification of CIMC connetivity with CIMC hostname | Yes | Yes
5 | ESXi installed on Local Storage or SAN | SAN | Yes
6 | ESXi version | VMWare ESXi 7.0.2 | Yes
7 | ESXi host Firmware version should be N-1 | Yes | Yes | Vendor recommendation communication to be attached
8 | Addition ESXI servers in respective vCenter Server | Yes | Yes
| Enable SNMP configuration if Rack server | Yes | Yes | Attach the sameple alert as an evidence
9 | NTP configuration = ntp1.myl.com & ntp2.myl.com | Yes | Yes
10 | DNS and Routing configuration | Yes | Yes
11 | License configuration for ESXi as per naming convention | Yes | Yes | Evidences to be shared from the Portal and vCenter
12 | Boot LUN Rename (esxiname_boot_lun) | Yes | Yes
13 | DvSwitch Creation as per the naming standard | Yes | Yes
14 | Add ESXi servers in distribution switch | Yes | Yes
15 | Management, vMotion and NFS kernel port groups to be created in vSS (Applicable wherever there are enough Physical adapters; primarily Cisco) | Yes | Yes
16 | Configure Port Channel with LACP on switch Ports - Needs to Create SR for Network Team | Yes | N/A
17 | If Portchannel configuration completed then Configure Teaming and Failover policy as - Route based on IP hash | Yes | Yes
18 | Create NFS Portgroup and VM kernal IP configuration (NFS IP should be in same IP segement as NFS VI server) | Yes | Yes
19 | Existing Datastore allocation to New ESXi server | Yes | Yes
20 | Configure Scratch Partition on Shared Storage | Yes | Yes
21 | Creation and configuration HA DRS cluster if not there | Yes | Yes
22 | DRS Set to fully automatic | Yes | Yes
23 | Configure EVC (Enhance Vmotion Compatiblity) for ESXi cluster | Yes | Yes
24 | Addition of ESXi host in HA DRS Cluster | Yes | Yes
25 | Modification of HA parameters in reservation to withstand 1 host failure (Override calculated failover policy to be selected if the cluster has morethan 2 nodes) | Yes | Yes
26 | Fix errors / Warning for ESXi hosts if any | Yes | Yes
27 | Verification of vMotion functionality | Yes | Yes
28 | Add ESXi server in monitoring (Task Assigned to Monitoring Team) | Yes | No
29 | Screenshot of the hostname, serial number, make model, location, L2 support group, Cluster to host relation from SNOW | Yes | Yes
30 | VIB's(enic and fnic drivers) version compatibility | Yes | Yes | Should be latest and recommneded by the vendor. Vendor confirmation requried to be attached in the Task
31 | Run the script for medicating the security vulnerability (/etc/init.d/slpd status; /etc/init.d/slpd stop; chkconfig slpd off; /etc/init.d/slpd status; /etc/init.d/sfcbd-watchdog status; /etc/init.d/sfcbd-watchdog stop; chkconfig sfcbd-watchdog off; /etc/init.d/sfcbd-watchdog status; /etc/init.d/wsman status; /etc/init.d/wsman stop; chkconfig wsman off; /etc/init.d/wsman status) | Yes | Yes
32 | ESXi and ssh timeout session set to 10minutes($vmhost=hostname; Get-VMHost $vmhos ¦ Get-AdvancedSetting UserVars.ESXiShellInteractiveTimeOut ¦ Set-AdvancedSetting -Value 600 -Confirm:$true; Get-VMHost $vmhos ¦ Get-AdvancedSetting UserVars.DcuiTimeOut ¦ Set-AdvancedSetting -Value 600 -Confirm:$true) | Yes | Yes
33 | Set IOPS value from 1000 to 1 (it should be round robin) for indivdual datastore(https://kb.vmware.com/s/article/2069356) | Yes | Yes
34 | Any port opening requried for ESXi to the backup server to do the backup over network | Yes | No
35 | Server to be added into respective vendor portal with the Nickname of server hostname and location to be verified | Yes | Yes | Screenshot to be obtained by capturing the support level, location of the server and the service contract status & validity
36 | Warranty support details should up to date In Vendror portal | Yes | No