## Server Build Sheet
Sl No | Build Date: 28-08-2024
1 | Parent RITM | Child RITM | RITM Transition | VM Name | IP Address | Cluster |  | VCenter | Date | Status
2 | RITM4915753(Win Build) | RITM4925517 | RITM4935838 | WBGVSIMATICP001 | 10.6.64.55 | BGHADRS001 |  | WB5VC001 | 2024-08-28 | Completed
3 | RITM4926384(Linux Build)
4
5 | Build Date: 02-09-2024 | (Windows Build)
6 | DC | vCPU | vRAM | Storage | Parent RITM | Child Build RITM | Trasition RITM | CTASK | Project Name/Server Description | Hostname | C | D | Page | OS | Build Engineer | Build N/W | Status
7 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939377 | RITM4944198 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922072 | W6OVSNATMP001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
8 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939380 | RITM4944227 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922075 | W6OVSNATMP002 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
9 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939376 | RITM4944242 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922081 | W6OVSNATMS001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
10 | 6O-IDC | 4 | 16 | 252 | RITM4922097 | RITM4939374 | RITM4944249 | TASK0324533 | GIDC Internal Infra Capacity Expansion - 2024- Automation Mid Server- SVCRITM4922086 | W6OVSNATMD001 | 120 | 100 | 32 | W2K22 | Keshavamurti KV | MFG | Completed
11
12 | Build Date: 02-09-2024 | (Linux Build)
13 | DC | vCPU | vRAM | Storage | IP Address | Cluster | Parent RITM | Child RITM | Transition RITM | project Name/Server Description | CTASK | Hosname | C | D | Page | OS | Build Engineer | N/W | Status
14 | 0B-GDC | 4 | 16 | 300 | 172.17.37.71 | 0BUAPPPRD001 | RITM4935184 | RITM4940342 | RITM4949251 | STOR management server | TASK0326044 | u0bvstormp01 | 120 | NA | 32 | RHEL 9.2 | Keshavamurti KV | Ent | Completed
15
16 | Build Date: 03-09-2024 | (Win22k Build)
17 | DC | vCPU | vRAM | Storage | Parent RITM | Child RITM | Trasition RITM | Project Name/Server Description | Hostname | C | D | E | T | L | Pagedrive | Sign Date | IP Address | OS | Build Engineer | Build N/W | Status
18 | 23-BRISBANE | 4 | 16 | 352 | RITM4913807 | RITM4947723 |  | KTLO - APAC - OSD/API Adhoc Requests-Carole Park Site 23 - BMS server build for DesigoCC-SVCRITM4913800 | W23VDCCBMSD001 | 120 | 100 | 100 | 0 | 0 | 32 | 2024-09-03 | 10.6.49.247 | W2k22 | Keshavamurti KV | MFG | Pending
19 | 23-BRISBANE | 4 | 16 | 402 | RITM4913807 | RITM4947724 |  | KTLO - APAC - OSD/API Adhoc Requests-Carole Park Site 23 - BMS server build for DesigoCC-SVCRITM4913795 | W23VDCBMSDBD001 | 120 | 100 | 100 | 25 | 25 | 32 | 2024-09-03 | 10.6.49.248 | W2k22 | Keshavamurti KV | MFG | Pending
20
21 | Manual Build Windows 2k19 | 2024-09-11
22 | Cluster | DC | vCPU | vRAM | Storage | Parent RITM | Child RITM | Transition RITM | Build Verification task | Project Name/Server Description | OS | Hostname | C Drive | D Drive | Pagedrive | VLAN | IP Address | N/W | CI Creation RITM | Priv acc | autologoff | Ci Relationship | Firewall Port Open | Change Request | Status
23 | E7HADRS001 | E7-DAL | 4 | 16 | 252 | RITM4936056 | RITM4957831 | RITM4978786 | TASK0328641 | MES EIH server - E7 | WE2K19 STD | WE7VMESEIHP001 | 120 | 100 | 32 | E7-DVPG-PC-MES-1126 | 10.4.37.106 | MFG Build | RITM4963040 | RITM4964353 | RITM4964366 | RITM4964392 | RITM4963222 | CHG0169182 | Closed
24
25 | Manual Build Windows 2k22 | 2024-09-12
26 | Cluster | DC | vCPU | vRAM | Storage | RITM/Project ID | Child RITM | Transition RITM | Project Name/Server Description | OS | Hostname | C Drive | D Drive | E Drive | T_TempDrive | L_LogDrive | Additional Drive | Pagedrive | VLAN | IP Address | SQL | Build Engineer | Build N/W | Status
27 | 5DHADRS003 | 5D-HUNGARY | 4 | 16 | 252 | RITM4942756 | RITM4964150 | RITM4969410 | Komarom - NexOn System Upgrade -App | W2K22 STD | W5DVNEXAPPP001 | 120 | 100 |  |  |  |  | 32 | 152 | 10.248.201.7 |  | Keshavamurti KV | ENT | Closed
28 | 5DHADRS003 | 5D-HUNGARY | 4 | 16 | 584 | RITM4942756 | RITM4964149 | RITM4969420 | Komarom - NexOn System Upgrade -DB | W2K22 STD | W5DVNEXDBP001 | 120 | 100 | 200 | 50 | 50 |  | 32 | 154 | 10.248.203.7 | SQL19 STD | Keshavamurti KV | ENT | Closed
29
30 | Automation Build ENT N/W | 19-09-2024-24-09-2024 | DM-Sreeraj p | CI/Handover Owner:Ravishankar Sethuraman
| DC | Cluster | Vcenter | vCPU | vRAM | Storage | RITM | Child RITM/CI Owner | Build Verification | Trasition RITM | Project Name/Server Description | Hostname | IP Address | OS | C Drive | D Drive | Add | Page | Build Engineer | Status
31 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973722 | TASK0330635 | RITM4978170 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2--SVCRITM4915920 | W0BVTWS008 | 172.17.36.174 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
32 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973730 | TASK0330635 | RITM4978186 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915934 | W0BVTWS009 | 172.17.36.177 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
33 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973727 | TASK0330635 | RITM4978191 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915944 | W0BVTWRPTS003 | 172.17.36.178 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
34 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973729 | TASK0330635 | RITM4978195 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915961 | W0BVTWD001 | 172.17.36.183 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
35 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973723 | TASK0330635 | RITM4978197 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915973 | W0BVTWD002 | 172.17.36.184 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
36 | 0B-GDC | 0BWAPPNPRD001 | w0bvc001 | 4 | 32 | 284 | RITM4916078 | RITM4973720 | TASK0330635 | RITM4978199 | Global TrackWise -upgrade-10.2.3.1 to 10.9 -Dev,Test , Edu and SB 2-SVCRITM4915982 | W0BVTWRPTD001 | 172.17.36.187 | W2K22 STD | 120 | 100 | 0 | 64 | Keshav | Closed
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319

## Server Upgrade Sheet
Sl No | RITM4930961 - D2 - Scale up and Extend Usage for Additional Doc Types & Sites | 2024-09-16
1 | Hostname | Vcenter | Child RITM | Current Version | Target Version | Change Request
2 | W0BD216MIGD004 | w0bvc001 | RITM4958581 | 2016 | 2022 | CHG0169373
3 | W0BD216MIGD005 | w0bvc001 | RITM4958583 | 2016 | 2022 | CHG0169374
4 | W0BD216MIGD006 | w0bvc001 | RITM4958576 | 2016 | 2022 | CHG0169375
5 | w6vagiacltp001 | w6vvc001 | RITM4958572 | 2012 | 2022 | CHG0169383/CHG0169384
6
7 | W0BD216MIGD004 | CHG0169373 | 18-Sep-24(06 AM to 06 PM) | Completed
8 | W0BD216MIGD005 | CHG0169374
9 | W0BD216MIGD006 | CHG0169375
10 | W6VAGIACLTP001(w6vvc001.myl.com) | CHG0169383 | 2012-2019 | Completed | yet to start | Manually Upgrade
11 |  | CHG0169384 | 2019-2022 |  |  |  | Need to remove snapshot manually
12
13 | 25-09-2024(10 AM - 10 PM)
14 | Parent RITM | Child RITM | RE: Intake ID - RITM4781454 - Mylan Canada Quality Control Lab Inventory Tracking Application 4 Server Builds -Signed off | Delivery Mgr: Meghashyam K M | Request Owner: Steve Lough, Abdul Shameem | OS-Version | Service Name
15 | RITM4918868 | RITM4966725 | W15myp001 | CHG0170100-Closed | I have been through all of the processes and performed a release to the server and everything is working.¦ Steve | 2019-2022 | Application Servers
16 | RITM4918868 | RITM4966731 | W15myp002 | CHG0170104-Closed |  | 2019-2022
17 | RITM4918868 | RITM4966733 | W15myp003 | CHG0170106-Closed |  | 2016-2022
18 | RITM4918868 | RITM4966728 | W0bmypwd001 | CHG0170101-Closed |  | 2016-2022
19 | RITM4922480 | RITM4969714 | w0bmypdbd001 | CHG0170102-Closed | Completed | 2016-2022 | DB Server
20
21 | 26-09-2024(10 AM- 10 PM)
22 | Parent RITM | Child RITM | D2 Dev Migration Servers OS upgrade | Delivery Mgr: Meghashyam K M | Request Owner: Janardhan Madhavarapu | OS-Version | Service Name
23 | RITM4930961 | RITM4958569 | W0BD216MIGD002 | CHG0170346 | Server and applications are running fine. Thanks and Regards, Komal Madan | 2016-2022 | Application Servers
24 | RITM4930961 | RITM4958567 | W0BD216MIGD007 | CHG0170350 |  | 2016-2022
25 | RITM4930961 | RITM4958565 | W0BD216MIGD008 | CHG0170351 |  | 2016-2022
26 | RITM4930961 | RITM4958584 | W0BD216MIGD009 | CHG0170352 |  | 2016-2022
27
28 | Comp Off
29 | 2024-09-28
30 | 2024-09-29
31
32 | Intake on 04-Oct-2024 | DM: Meghashyam M | D2 Dev Migration Servers OS upgrade ¦ Activity Scheduled on 09th Oct 2024 10AM-10PM ¦ Requestor: Janardhan Madhavarapu |  |  | Environment
33 | Parent RITM | Child RITM | Hostname | Change Requests | Current version | Testing Servers
34 | RITM4930961 | RITM4958563 | W0BD216MIGT004 | CHG0171045 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | CHG0168951-OS Upgrade.. reference change.
35 | RITM4930961 | RITM4958571 | W0BD216MIGT005 | CHG0171046 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | For the OS Upgrade Task Steps:
36 | RITM4930961 | RITM4958560 | W0BD216MIGT006 | CHG0171047 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Open the Service Catalog.
37 | RITM4930961 | RITM4958575 | W0BD216MIGT007 | CHG0171048 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Select OS In-Place Upgrade (Windows).
38 | RITM4930961 | RITM4958561 | W0BD216MIGT008 | CHG0171049 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Fill in the required details: Vcenter name, Hostname, Downtime, ISO path, and OS name.
39 | RITM4930961 | RITM4958570 | W0BD216MIGT009 | CHG0171050 | Microsoft Windows Server 2016 STD- 2022 STD |  |  | Submit the request; this will generate an RITM with a Change Request number.
40 | [7 empty] | Please forward the RITM to the technical approver (Venu).Put the server in maintainance mood manually by maintainance schedules.
41 | Intake on 14-Oct-2024 | DM: Meghashyam M | D2 Dev Migration Servers OS upgrade ¦ Activity Scheduled on 17th Oct 2024 10AM-10PM ¦ Requestor: Janardhan Madhavarapu |  |  | Environment |  | For the OS Upgrade Task Steps:
42 | Parent RITM | Child RITM | Hostname | Change Requests | Current version |  |  | First, check the available space on the C drive; ensure there is a minimum of 35GB.
43 | RITM4930961 | RITM4958578 | W0BD216MIGD001 | CHG0171655 | Microsoft Windows Server 2016 STD- 2022 STD | Dev |  | If there is insufficient space, clear any unwanted files.
44 | RITM4930961 | RITM4958577 | W0BD216MIGD003 | CHG0171659 | Microsoft Windows Server 2016 STD- 2022 STD | Dev |  | Monitor the C request. Close the App and DB service tasks; snapshots will be taken care of automatically.
45 | RITM4930961 | RITM4958582 | W0BD216MIGT001 | CHG0171658 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Mount the ISO to the VM and start the upgrade process.(Automatically)
46 | RITM4930961 | RITM4958566 | W0BD216MIGT002 | CHG0171656 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Monitor the status in the VM through the LogView folder using Script1.
47 | RITM4930961 | RITM4958564 | W0BD216MIGT003 | CHG0171657 | Microsoft Windows Server 2016 STD- 2022 STD | Testing Servers |  | Need to monitor the Change Request and Reuest Pending Change RITM's
48 | [7 empty] | Close the App and DB service CTasks.
49 | [7 empty] | Inform the server owner to start the application services and check the status.
50 | [7 empty] | Attach the post-upgrade activity details, including: 1. Hostname and Properties, 2. Drive Details, 3. Screenshot
51 | [7 empty] | Post upgradation completed
52 | [7 empty] | 1. Upgrade the VMware Tools.
53 | [7 empty] | 2. Change the hardware compatibility version to the latest version.
54 | [7 empty] | 3. Update the Guest OS version in the VMware Options console (OS Container).
55 | [7 empty] | 4. Inform the Patch team to push the latest updates.
56 | [7 empty] | 5. Uninstall the Carbon Black Agent from the old servers 2022 servers no need this agent.
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370

## Sheet1
Sl.No | Oct 2024 Expense | INR | Status | Remarks
1 | Ration | 3740 | Done
2 | House Rent | 12500 | Done | 6k cash
3 | Car Loan | 17666 | Done
4 | Mutual Fund | 14000 | Done
5 | Metro Recharge | 900 | Done
6 | Credit card | 2500 | Done
7 | Medicine | 1200 | Done
8 | Bglkt Expense on 9th Oct | 5500 | Done
9 | Moved to SBI | 20000 | Done
10 | Scooty Petrol | 1000
11 | Total | 75266
12 | Salary | 100301
13 | Exp | 49766
14 | Balance | 50635